## Sheet1
High Level Plan |  | Task List | Completion | Details
Jan Week 3 | Research on Graphics Library | Find a Graphics library to use for Dining Arrangement | Check | Decidced to use Bonsai as Library should be able to work, had to switch libraries to Raphael struggled with Bonsai
Jan Week 4 | Research on Processing/Bonsai | Create Moavble shapes to lock in Place | Check | Can now add tables to the canvas
Feb Week 1 | Beginning work on the "Create Dining Arrangement Mode" | Let user save their Dining Arragement | Check | Database is set up properly just need to add some coumns
Feb Week 2 | Have a working "Create Dining Arrangement Mode" | Create basic android UI Menu (View) | Check | View Mode has been created and pulls from the database on creation
Feb Week 3 | Begin Setting up a Database to record Dining Arrangements | Find a way to add a timer to represented tables (color code) | Check | Colors Represent Time Now
Feb Week 4 | Do Finishing Touchings on Database Implementation | Need to firgure out animation and how to drag tables for creator | Check | Found Dragger method to handle animations
March Week 1 | Create View Mode to load from a database | Enable User to Reserve | Check | User can reserve and submit their info to a database
March Week 2 |  | Reservation Kick | Check | Host can kick users on the list using the dropdown menu
March Week 3 | TODO | Add Time Colors | Check | Can Calculate Time just have to add in colors now
March Week 4 | TODO | Let User connect to their own database | Incomplete | Due to inconveniences in the application server
April Week 1 | TODO | Add Wall Boundaries | Incomplete | Did not complete. Did not see the the impotance in it
April Week 2 | TODO | Assign Employees / Seats to Tables | Check | Added Coulmn to Database and now Track properly
|  | Create the Android App | Check | The Application was created but is a little more simplistic than Orginally intended
|  | BUG Update Old info when saved to DB | Check | Changed the Loop in how data was being recorded and updated
|  | Finished setting Data on load | Check | Can now loa database on load
|  | Allow User to Change Server | Check | Added a Dropdown menu that connects to the employee database to let user assign servers to tables
|  | Add Seats to Database | Check | Added seats to the table database